## SaaS RACI
DRAFT v2.2 11/26/18 |  | Legend: A = Accountable for the work getting done; often much of the work with "R" roles. R = Responsible; performs heavy lift of work. C = Consulted; may provide feedback that is considered. I = Informed; no feedback requested. Blank = N/A for that task.
Play | Task | Roles
|  | Business / Requestor | AMO (4) | Demand Mngmt. (Bill/Amy) | PSF Drew | IT Cloud Security (Royce, Mike) | SaaS ISO (Charles S. Jackson) | CPO (Rob Disko) | EPMO IA (Ruchika, Rebecca) | EPMO AO (to approve ATO) Bill James | TAC | ESECC | Vendor
Play 1: Define the Need / Determine if the Solution is SaaS (incl. microconsulting) | Conduct a discovery sprint with real users | A | C | R | C | C |  |  | I |  | I |  | I
| Fill out VA Intranet SaaS Inquiry Form | A | I | I | C | C
| Complete VIPR Epics | A | R | C | I | I |  |  | I |  | I |  | C
| (As needed) Conduct an analysis of alternatives (AoA) and identify the proposed product solution | R | C | R | A | C | [6 empty] | C
| OIT PSF to validate solution is SaaS during SaaS inquiry call (and note this in VIPR system) | R | I | I | A | R |  |  | I |  |  |  | C
| Determine if SaaS product / infrastructure has started FedRAMP compliance (include link) | R | C | C | C | A |  |  | I |  |  |  | R
| Follow guidance provided by IT Cloud Security Team for FedRAMP (add link from Mike C.) | A | I | I | C | R |  |  | I |  |  |  | R
| Follow guidance from PSF and IT Cloud Security Team for SaaS PWS (re security, SLAs, etc.) | A | I | I | R | R |  |  | I |  | C |  | I
| Award SaaS micro-purchase for MVP | A | I | I | R | I |  |  | I |  | R |  | I
| All SaaS projects must have a VIPR ID & be marked as "SaaS" in VIPR | A | C | R | I | I |  |  | I |  | I
Play 2: Complete VA's Unified Intake (VIPR) Process | Complete the VIPR process and workbook | A | C | R | I | I |  |  | I |  | I
| OIT Cloud Security Team to complete SaaS Security Assessment (requires product to be identified) | R | C | C | R | A |  |  | C |  | I |  | R
| Prepare for SaaS microconsulting to test SaaS minimum viable product (MVP) | A | I | I | R | C |  |  | I |  | C |  | I
| Prepare for SaaS procurement using PWS guidance (sole source, SLA, etc.) | A | I | I | R | C |  |  | I |  | R |  | I
Play 3: SaaS Security Assessment | Provide information on current FedRAMP status and SaaS system for security assessment | A | I | I | C | R | C | I | I |  |  | I | R
| Complete security assessment | I | I | I | R | A | I | I | I |  |  |  | C
Play 4: Procure SaaS | Incorporate lessons learned in PWS from SaaS microconsulting MVP testing | [9 empty] | C |  | C | bar: A; C to R
| Manage / Award SaaS procurement | [9 empty] | A |  | I | bar: A to R; I
Play 5: Complete ATO Tasks | Ensure ESECC approval as needed (for connections to VA systems) | R | I | I | A | C |  |  | C | I | I | R | I
| VA issues FedRAMP ATO for SaaS / baseline for VA information system | I |  |  | C | A | I | I | R |  |  | I | I
| VA information system completes RMF requirements | I | i | I | C | C | A | I | R | A |  | I | I
| Follow VA's ATO process: VA’s Authorization Requirements Standard Operating Procedures v3.22 (June 2018) | R | I | I | A | C | R | R | R | A |  | C | R
| VA Information System ATO | I |  |  | C | C | I | A | R |  |  | I | I
Play 6: Implement SaaS | Implement product in sprints (product owner / scrum master task guidance from PSF) (add link) | I R: A/R; C A: A/R |  |  | R
| Deploy communications, change management, and training | [11 empty] | C | bar: I R; C A
| Ensure VIP compliance | I R: A/R; C A: A/R |  |  | R
Play 7: Manage Operations / Measure Outcomes | Fix bugs / report on SLAs performance using automated monitoring and testing | [9 empty] | I |  | A | bar: I R; C A
| SaaS System Owner | [11 empty] | R | bar: I R; C A
| Manage product / system roadmaps (based on user research and VA requirements) | I R: R; i I: I; I I: I; C A: I; C C: C |  |  | A
| Report outcomes | I R: A; i I: I; I I: I; C A: I; C C: C | I |  | C
| Ongoing usability testing / user research | I R: A; i I: I; I I: I; C A: I; C C: R |  |  | C
| Provide VA requirements from user research | [11 empty] | R | bar: I R; C A