## SaaS RACI
DRAFT v2 11/9/18 (validated by PSF and IT Cloud Security Team)
VA SaaS Playbook RACI
Play | Task | Roles
|  | Business / Requestor | AMO | Demand Management | PSF | IT Cloud Security | CPO (Rob Disko) | EPMO IA | EPMO AO (to approve ATO) Bill James | TAC | ECSSB | Vendor
Play 1: Define the Need & Determine if the Solution is Saas
| Conduct a discovery sprint with real users | A | C | I | R | C |  | I |  | I |  | I
| Complete VIPR Epics | A | R | I | I | I |  | I |  | I |  | C
| AoA and identify the proposed product solution | R | C | I | A | C
| OIT PSF to validate solution is SaaS (and note this in VIPR system) | C | C | C | A | C |  | C |  | I |  | C
| Determine if SaaS product / infrastructure has started FedRamp compliance (include link) | C | C | C | R | A |  | C |  | I |  | C
| Follow guidance provided by IT Cloud Security Team for FedRamp (add link from Mike C.) | A | R | I | R | R |  | C |  | I |  | C
| Follow guidance from PSF and IT Cloud Security Team for SaaS PWS (re security, SLAs, etc.) | A | R | I | R | R |  | C |  | C |  | C
| Award SaaS micro-purchase for MVP | A | I | I | R | I |  | I |  | R |  | I
| Gather feedback and lessons learned on SaaS MVP | A | I | I | R | I |  | I |  | I |  | R
| All SaaS projects must have a VIPR ID & be marked as "SaaS" in VIPR | A | C | C | I | I |  | I |  | I |  | I
Play 2: Complete VA's Unified Intake (VIPR) Process including a SaaS Assessment
| Complete the VIPR process and workbook | A | C | R | I | I |  | I |  | I
| OIT Cloud Security Team to complete SaaS Security Assessment (requires product to be identified) | C | C | C | R | A |  | C |  | I |  | R
| Prepare for SaaS micro-purchase for minimum viable product (MVP) | R | I | I | A | R |  | I |  | C |  | I
| Prepare for SaaS procurement (sole source, SLA, etc.) | A | I | I | R | R |  | I |  | R |  | I
Play 3: Procure SaaS
| Award SaaS procurement | C | I | I | C | I |  | I |  | A |  | I
Play 4: Get ATO
| Ensure ESECC approval as needed (for connections to VA systems) | R | I | I | C | C |  | R | I | I | A | I
System for SaaS ATO - system TBD
| Approve ATO for SaaS product (e.g., Qgenda results in residual baseline) | I | i | I | R/A | R | I | C | A | I | I | I
| Follow VA's ATO process: VA’s Authorization Requirements Standard Operating Procedures v3.22 (June 2018) | R | I | I | C | C | R/A | R | A | I | C | R
Play 5: Implement SaaS / Ensure VIP Compliance
| Implement product in sprints (product owner / scrum master task guidance from PSF) (add link) | A/R | I | I | A/R | I |  | I |  | I |  | R
| Deploy communications, change management, and training | A | I | I | C | I |  | I |  | I |  | C
| Ensure VIP compliance | A/R | I | I | A/R | I |  | I |  | I |  | R
Play 6: Manage Operations / Sustainment
| Fix bugs / report on SLAs performance using automated monitoring and testing | C | I | I | I | I |  | I |  | I |  | A
SaaS System Owner (just for cloud service) | bar: I R
| Manage product / system roadmaps (based on user research and VA requirements) | R | I | I | I | C |  | C |  | I |  | A
Play 7: Measure Outcomes / Ongoing Improvement
| Report outcomes | A | I | I | I | C |  | I |  | I |  | C
| Ongoing usability testing / user research | A | I | I | I | R |  | I |  |  |  | C